## Defects
Sl No | Submitted By | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Status(Open/Closed) | Remarks
1 | Intern | Document ingestion pipeline failed silently for PDFs with scanned/image-only pages — no error was raised | Sprint 1 | Self | Logical | Added pre-check to detect image-only PDFs; raises a clear user-facing error with suggestion to use OCR | Closed | OCR support flagged as future enhancement
2 | Intern | Text chunking produced chunks with zero length when consecutive whitespace-only lines were encountered | Sprint 1 | Self | Logical | Added whitespace stripping and minimum chunk-length validation before adding chunk to the list | Closed
3 | Intern | Vector database connection string was hardcoded; caused failure when moved to a different environment | Sprint 1 | Self | Standards | Moved all connection parameters to environment variables using a .env file and python-dotenv | Closed
4 | Intern | Retrieved document chunks were not always relevant for certain user queries — cosine similarity scores were low | Sprint 2 | Self | Logical | Tuned embedding model to 'text-embedding-ada-002'; adjusted chunk size to 512 tokens with 50-token overlap | Closed | Retrieval relevance improved significantly
5 | Intern | Duplicate document chunks were being stored in the vector DB when the same file was ingested more than once | Sprint 2 | Self | Logical | Added document fingerprinting (MD5 hash) before ingestion; existing hashes are skipped | Closed
6 | Intern | LLM API call timed out for long documents when all retrieved chunks were concatenated into a single prompt | Sprint 2 | Self | Logical | Limited context window to top-3 most relevant chunks; added token counting to stay within LLM limits | Closed
7 | Intern | Generated answers did not include proper source citations for some responses when multiple chunks matched | Sprint 3 | Self | Standards | Implemented chunk metadata tracking; source file name and page number appended to every generated answer | Closed | Citation issue resolved
8 | Intern | System hallucinated an answer for a query with no relevant documents in the corpus instead of declining | Sprint 3 | Self | Logical | Added similarity score threshold; if best score < 0.75 the system returns 'I don't have enough information' | Closed | Hallucination guard implemented
9 | Intern | Follow-up questions lost context when the conversation exceeded 5 turns due to missing history truncation logic | Sprint 3 | Self | Logical | Implemented sliding-window conversation history (last 5 turns retained); older turns pruned gracefully | Closed
10 | Intern | LLM sometimes repeated the user's question verbatim at the start of every response | Sprint 3 | Self | Standards | Updated system prompt to explicitly instruct the LLM not to echo the user's question in the response | Closed
11 | Intern | Chat interface submit button remained active while a response was loading — caused duplicate API calls on double-click | Sprint 4 | Self | User Interface | Disabled submit button and showed spinner immediately on click; re-enabled after response is fully received | Closed
12 | Intern | Long responses overflowed the chat bubble container on narrow/mobile screen widths | Sprint 4 | Self | User Interface | Applied CSS word-break and overflow-wrap rules to chat bubbles; tested on 320 px and 768 px breakpoints | Closed
13 | Intern | No loading indicator shown between query submission and response arrival — users re-submitted thinking it failed | Sprint 4 | Self | User Interface | Added animated 'Thinking…' typing indicator that appears immediately after submission and hides on response | Closed
14 | Intern | Conversation history was not cleared between browser sessions — old context leaked into new conversations | Sprint 4 | Self | Logical | Stored conversation state in session-scoped variables on the backend; frontend sends a session token per visit | Closed
15 | Intern | Deployment failed on cloud environment because required Python packages were missing from requirements.txt | Sprint 5 | Self | Maintainability | Ran 'pip freeze > requirements.txt' in a clean virtual environment and committed updated file to repo | Closed
16 | Intern | API keys were accidentally committed to the public repository in a config file | Sprint 5 | Self | Standards | Revoked and rotated all keys; added .gitignore rules for .env files; added pre-commit hook to scan for secrets | Closed | Critical — immediate action taken
17 | Intern | System response time exceeded 15 seconds for queries that retrieved chunks from large multi-hundred-page PDFs | Sprint 5 | Self | Logical | Introduced asynchronous chunk retrieval and caching of frequently queried embeddings | Closed | Average latency reduced to < 6 s
18 | Intern | Vector database index was rebuilt from scratch on every application restart — caused multi-minute cold start | Sprint 5 | Self | Maintainability | Added index persistence: index is saved to disk after ingestion and loaded on startup if it already exists | Closed
19 | Intern | Concurrent user queries caused race conditions in the shared in-memory conversation history dictionary | Sprint 6 | Self | Logical | Replaced shared dictionary with thread-local storage; each request now has an isolated history object | Closed
20 | Intern | Evaluation accuracy script threw a KeyError when ground-truth Q&A CSV had an extra trailing comma | Sprint 6 | Self | Others | Added CSV parsing with error handling and strip() on all field values; validated against 20-row test set | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others